## D01
	MAIN WORKING CONVERSATION
	https://chatgpt.com/c/686be4c8-99a8-8006-b585-8df1078a3ebe

Commit b59409e	FUNCTIONALITY	FILES	METHOD/NOTES		Set a milestone or milestones
	Add Package in API.csproj (designer)				Research Commit Map and Highlight
	launchsettings.cs		change address		Read Actual Commit History on Reference Project
	API.http		does this happen automatically?			Extract on this file the functionality, files and methods or comments
	appsettings.development.json					Order functionality
	AppUser.cs		initial model		Develop functionality one by one and test in postman (with .net and angular debugging)
	Program.cs		add sql lite
	DataContext.cs		Add DbSet
	UsersController.cs		GetUser() GetUsers()
Commit fe59003	Program.cs		Add CORS Support

	✅ Initial Setup

Commit 119a004	FUNCTIONALITY	FILES	METHOD/NOTES
	Add Packages in API.csproj
	AppUser.cs		register() login() userexists()
	LoginDTO.cs
	RegisterDTO.cs
	UserDTO.cs
	Program.cs
	ApplicationServiceExtensions.cs
	IdentityServiceExtensions.cs
	Run Migrations
	ItokenService.cs
	TokenService.cs
	AppSettings.json
	WeatherForecastController.cs
	AccountController.cs
	BaseAPIController.cs
	UsersController.cs

	✅ Setup Postman and Test Controller Functionality

	✅ Configure Identity in Program.cs and StartupExtensions.cs
	✅ Setup JWT Bearer authentication with token validation
	✅ Create or review TokenService.cs
	✅ Add RoleManager, UserManager, and role claim logic
	✅ Seed roles (Admin, Freelancer, Client) in Seed.cs
	✅ Test generating a token with a known user and inspect claims

## D02
	MAIN WORKING CONVERSATION
	https://chatgpt.com/c/686be4c8-99a8-8006-b585-8df1078a3ebe

Commit f28d3dc	FUNCTIONALITY	FILES	METHOD/NOTES		Set a milestone or milestones
	app.component.ts	make http request			Research Commit Map and Highlight
	app.config.ts	add http provider, what is it?			Read Actual Commit History on Reference Project
Commit fe59003	add https with mkcert and pem files					Extract on this file the functionality, files and methods or comments
	angular.json	this has to do with certificates, also bootstrap styles				Order functionality
	demo/DatingApp/client/install-key.pem	certificates			Develop functionality one by one and test in postman (with .net and angular debugging)
	demo/DatingApp/client/install.pem	certificates
	package.json	bootstrap ngx bootstrap and fontawesome
	demo/DatingApp/client/ssl/localhost-key.pem
	demo/DatingApp/client/ssl/localhost.pem

	app.component.html	print users and their ids
	app.component.ts	print users and their ids

No commit	Debug Angular Try first time

	✅ Basic Angular Setup, Bootstrap etc
	✅ Debug Angular with the Chrome Dev Tools Source Tab

Commit fbfcf7b	FUNCTIONALITY	FILES	METHOD/NOTES
	API.csproj	Add identity package
	DataContext	adapt data context to identity
	Seed.cs	review whole file, - add seed.cs and seed data file
	AppRole.cs	Add AppRole Entity
	AppUser	Adapt AppUser to identity
	AppUserRole	important to set approle and appuser to have many to many relationship
	IdentityServiceExtensions	add Program.cs support for roles with identity
	TokenService	fix old problem
	run migrations
	AccountController	adapt the controller to identity
	MessagesController	add fix to controller

	✅ Configure Identity in Program.cs and StartupExtensions.cs
	✅ Setup JWT Bearer authentication with token validation
	✅ Create or review TokenService.cs
	✅ Add RoleManager, UserManager, and role claim logic
	✅ Seed roles (Admin, Freelancer, Client) in Seed.cs
	✅ Test generating a token with a known user and inspect claims

## D03
	MAIN WORKING CONVERSATION
	https://chatgpt.com/c/686be4c8-99a8-8006-b585-8df1078a3ebe

Commit caf64e0	FUNCTIONALITY	FILES	METHOD/NOTES		Set a milestone or milestones
	app.component.ts	add navComponent reference			Research Commit Map and Highlight
	nav.component.html	structure for nav bar – must generate component			Read Actual Commit History on Reference Project
	nav.component.ts	review just in case but out of the box code here				Extract on this file the functionality, files and methods or comments
Commit 1c7d982	user.ts	client user modl				Order functionality
	account.service.ts	login() register() logout()			Develop functionality one by one and test in postman (with .net and angular debugging)
	app.component.html	add home component
	app.component.ts	ad HomeComponent reference, setCurrentUser() to call accountservice().set (not sure how this works)
	app.config.ts	add animations provider
	home.component.html	structure for register button wireframe
	home.component.ts
	nav.component.css (name this freelancerNav component) – since ill create a clientNav component later	add styles
	nav.component.html	nav bar structure
	nav.component.ts
	register.component.html
	register.component.ts	register() cancel(register)()

Commit 7c6316e	FUNCTIONALITY	FILES	METHOD/NOTES
	angular.json	added styles for toastr and boostrap
	package	add bootswatch and toastr
	auth.guard.ts	added guard to only allow current users to access certain components
	account.service.ts	added signal for current user on login() register() and logout()
	app.component.html	added router to app.component
	app.component.ts	add cureent user to account service – ask gpt to clarify
	app.config.ts	add toastr provider
	app.routes.ts	see how can I adapt – ask gpt how to create a router file to adapt to current setup (maybe just HomeComponent) bare bones, will need to expand later
	nav.component.html	will need to add routerLinks to components once I create them, personalize dropdown
	nav.component.ts	modify login() and logout() add relevant properties
	register.component.ts	add toastr to register()
	profile.component.css / html / ts	create component

## D04
	MAIN WORKING CONVERSATION
	https://chatgpt.com/c/686be4c8-99a8-8006-b585-8df1078a3ebe

Commit 5e56f7d	FUNCTIONALITY	FILES	METHOD/NOTES		Set a milestone or milestones
	BuggyController.cs				Research Commit Map and Highlight
	RegisterDTO.cs				Read Actual Commit History on Reference Project
	ApiExceptions.cs					Extract on this file the functionality, files and methods or comments
	ExceptionMiddleware.cs					Order functionality
	Program.cs				Develop functionality one by one and test in postman (with .net and angular debugging)
Commit 9fed274	AppUser.cs
	Photo.cs	ask gpt if photo should be a separate entity – should it be one to one, and then establish a one to one with projects which should retrieve the photo of the associated freelancer or client
	AccountController.cs

Commit c0463c2	FUNCTIONALITY	FILES	METHOD/NOTES
	error.interceptor.ts
	app.config.ts
	app.routes.ts
	Not-found.component.html
	Not-found.comonent.ts
	Server-error.component.html
	Server-error.component.ts
	Test-errors.component.html
	Test-errors.component.ts
	nav.component.html	freelancer nav component

	Error handling

## D05
DAY 05	Work on backend Repositories (backend day)
Commit dcf7194	FUNCTIONALITY	FILES	METHOD/NOTES
	UserRepository	full file
	PhotosSeedData (new file)	use random user photos
	Seed.cs	add Photos Seed Data
	Photo.cs	data annotation
	ApplicationServiceExtensions	AddScoped User Repository
	DateTimeExtensions	CalculateAge()
	IuserRepository
	Program.cs	compare with what I have

Commit 3b11556	FUNCTIONALITY	FILES	METHOD/NOTES
	API.csproj	add automapper package
	UsersController	update with Repository Pattern
	MemberDTO	study to see what to put here
	PhotoDTO	study to see what to put here
	UserRepository	full file, really think this through
	ApplicationServiceExtensions	Add Automapper service
	AutoMapperProfiles	Map AppUser to MemberDTO
	IuserRepository

Commit b08267e	FUNCTIONALITY	FILES	METHOD/NOTES
	member.ts	study to see what to put here
	photo.ts	study to see what to put here
	user.ts	study to see what to put here

	Repository Pattern

## D06&07
DAY 06	Work on Profile Component
Commit f54b38f	FUNCTIONALITY	FILES	METHOD/NOTES
1	angular.json	enviornment switch
1	jwt.interceptor.ts	attach jwt to http requests
1	account.service.ts	small url change
1	members.service.ts	develop members service and methods
1	app.config.ts	attach interceptor
1	routes.ts	add username to profile route
1	Test-errors.component.ts	small url change
1	home component	delete onINit get Users (think I already did it)

2	Memeber-detail component css html ts	based on this develop further the profile page

1	environment.development.ts	write it out
1	environment.ts	write it out

	Work on Portofio Item in the Backend
Original Content	FUNCTIONALITY	FILES	METHOD/NOTES
1	AppUser Entity
1	Data Context
1	PortofolioItem Entity with Migrations
2	PortofolioItem DTO
2	Users Repository
2	Iuser Repository
2	Automapper Profiles
2	portoflioitem.ts
2	Seed.cs
3	Test API call to retrieve PortofolioItems

	Profile View Part I

Commit f54b38f
1	Member-card component.css, html, ts	might map it to project-card, or portfolioitem-card or something similar later on
1	Member-list component.css html ts	might map it to profile:username section to display portofolio items
	Integrate the portoflio-item card and portfolio-list components into the profile:username view

Commit cdb867c	package.json	added cdk and ng gallery (which I wont use)
	Member-card component html	added default photo
	member detail html	see if anything useful here
	member detail component ts	gallery (which I wont use)
	user.png	add photo
	styles.css	tabset styles add just in case

Past work	plus nav bar for client

	Profile View Part II

## D08
DAY 08
	Brainstorm Projects entity and relationships					implement on the backend, entities, dbcontext, migrations, dtos, seeds, user repository, test api
					think of the properties of the project entity like skills, description, title, photo url, clientuserid and freelanceruserid as foreign keys, isassigned boolean, ask gpt if there are more considerations for this entity
	Implement Projects such that they load when the client user profile displays					one to many and one to many
	as published projects

	User should have Freelancer Projects and Client Projects					display on the front end
		only users with role of Client have Client projects and so on					model, profile component implement profile project list component and profile project item component, similar to the two ive created before
					copy design from previous items
	when user with role of client goes to profile, the client projects load					implement delete functionality for profile-items and for profile project items simple button
					will include backend delete requests
	later on when a freelancer browses projects the client projects load

	later on when a freelancer is accepted for a client project it becomes a freelancer project

	Profile View Part III
	A		B		C
	✅ Project.cs		Create project.ts		IportfolioItemRepository
	✅ Modify User.cs		update member.ts		PortfolioItemREpository
	✅ Update DataContext + Fluent Validations & run Migrations		create profile-project-list component html ts (input + loop through profile-project-item)		ApplicationServiceExtensions
	✅ Modify Seed.cs (only if you need test data)		create profile-project-item compoment html ts (input + display details)		PortfolioItemController Delete Endpoint
	✅ Create ProjectDTO		modify profile component ts (fetch member, pass member.clientprojects and member.freelancer projects into app profile projects list)		Test on the API, login a user, user their JWT to send a Delete Request for a Known
	✅ Modify UserDTO		test in the browser		Portfolio Item that belongs to them
	✅ Update AutoMapperProfiles
	✅ Test the API in Postman

	Display Projects for Client on Profile – Backend		Display Projects for Client on Profile – Frontend		Delete Portfolio Items for Freelancers – Backend

## D09
DAY 9

Delete Projects for Clients – Backend			Delete Portfolio Items for Freelancers – Front End			Delete Profile Project Items for Clients – Front End
A			B			C
IprojectRepository			Portfolio-item.Service			Project.Service	delete project call to http
ProjectRepository			Profile Component			Profile Component	Output variable with event emitter of type number, and delete on click event on html
ProjectController			Portfolio List Component			Profile Project List Component	add a method to remove the item from the array, add html code
ApplicationServiceExtensions			Portfolio Item Component			Profile Project Item Component

## D10
DAY 10	PROFILE UPDATE BACK AND FRONT + STUDY DAY 10 COMMITS FROM COMMIT MAP					PLUS GETTING THE MEMBER DATA FROM THE BACKEND TBD

DAY 10
STUDY THIS FIRST
	Commit e5e8a94	userController.cs	UpdateUser() - for the edit form	A1		Commit 92e82dc	angular.json	added loading animation css reference	loading
		MemberUpdateDTO	define fields	A2			package.json	added ngx-spinner (loading dependency)	loading
		Automapper Profiles	Add mapping	A3			loading.interceptor.ts	activate loading animation	loading
		Prevent-unsaved-changes-guard		A4			busy.service.ts	logic for loading animation	loading
		app.routes.ts	member edit will be profile edit	A5			members.service.ts	modify getMember() getMembers() and updateMembers() to implement signals and cache	B1
		Memeber-edit-component.css	styles	A6i			app.component.html	add spinner for testing	loading
		Memeber-edit-component.html	study how this transfers to freelancer profile	A6ii			app.component.ts	add spinner import to ts file	loading
			study how this transfers to client profile	A6ii			app.config.ts	add loading interceptor to providers, and import providers for loading animation	loading
		Member-edit-component.ts	basic boilerplate code	A6iii			Member-edit-component.html	changed text	B2 I
		nav component html	add routerlink	A7			Member-edit-component.ts	updateMember() now calls the member.service updateMember() method	B2 ii
				Member-list.comonent.html	user the member service members() signal on member-list component to provide a list of members	B3
				Member-list-component.ts	use the signal to check if loading members is necessary	B3

THEN IMPLEMENT		DONT TAKE CARE OF THE PHOTO YET

	BACKEND UPDATING PROFILE			FRONT END UPDATING PROFILE			FRONT END UPDATING PROFILE

	IuserRepository	Nothing here – not necessary, controller handles all		Member Service	updateMember() getMembers() and getMember()	B1	Profile Edit Client Component		A6i ii and iii, B2
	User Repository	Nothing here – not necessary, controller handles all		Profile Edit Freelancer Component		A6i ii and iii, B2	routes.ts		A4
	User Controller	UpdateUser()	A1	routes.ts		A5	Profile Component	navigation links	A5
	MemberUpdateDTO		A2	Profile Component		A7
	Automapper Profiles		A3	Prevent-unsaved-changes-guard.ts		A4
	Test Endpoint on Postman

## D11
			THINGS WE DONT NEED TO DO
BACKEND FUNCTIONALITY			WE FETCH THE ITEMS AND PROJECTS VIA THE MEMBERS SERVICE (ALREADY IMPLEMENTED)
			WE FETCH A MEMBER AND ITS RELATED DATA
CREATE PORFOLIO ITEMS
CREATE PROJECTS
UPDATE PORTFOLIO ITEMS
UPDATE PROJECTS

CREATE PI		UPDATE PI			CREATE P		UPDATE P
IporfolioItemRepository		In Tandem			IprojectRepository		In Tandem
PortfolioItemRepository		In Tandem			ProjectRepository		In Tandem
PortfolioItemController		In Tandem			ProjectController		In Tandem
CreatePortfolioItemDTO		UpdatePortfolioItemDTO			CreateProjectDTO		UpdateProjectDTO
AutomapperProfile		AutomapperProfile			AutomapperProfile		Automapper Profile
ApplicationServiceExtensions		-			ApplicationServiceExtensions		-
Test API Functionality (Create a Portfolio Item)		Test API Functionality			Test API Functionality		Test API Functionality

Create Receives and Id for the User (property of the Portfolio Item Entity)		Update Doesnt			Create Receives an Id for the Related User		Update Doesnt

## D12
			For the Create and Update think of how they could be implemented on the same screen – portfolio edit component, project edit component
	CREATE ENDPOINT		Create Portfolio Item Backend + Create Profile Project Item Backend + Create Portfolio Item Front End + Create Profile Project Item Front End
	UPDATE ENDPOINT		Update Portfolio Item Backend + Update Profile Project Item Backend + Update Portfolio Item Front End + Update Profile Project Item Front End

	DAY 12	2 FRONT END COMPONENTS (PROJ CREA&EDIT AND PORTITEM CREA&EDIT)						PLUS GETTING THE DATA FROM THE BACKEND TBD

	FIRST DO CREATION THEN DO EDITION					FIRST DO CREATION THEN DO EDITION
	FRONT END – PORTFOLIO ITEM CREATION AND EDITION					FRONT END – PROJECT CREATION AND EDITION

	Portfolio Item Edit Component		2			Project Edit Component
2	Portfolio Item Create Component					Project Create Component
3	routes (implement prevent unsaved changes guard)		3			routes (implement prevent unsaved changes guard)
4	Maybe receive information from Portfolio Item Component		4			Maybe receive information from Profile Project item component
1	Portfolio Item Service (two methods create and update)		1			Project Service (two methods create and update – remember to pass the project id on update => see endpoint signature on backend)

## D13
LOADING INDICATORS AND CLOUDINARY PART I

Commit 92e82dc	angular.json	added loading animation css reference	loading		Commit a14b9d2	Stop tracking appsettings.json	appsettings.json	file deleted (probably added to gitignore)
	package.json	added ngx-spinner (loading dependency)	loading
	loading.interceptor.ts	activate loading animation	loading			Added Cloudinary Service Part I (Photo Service and Cloudinary Settings)
	busy.service.ts	logic for loading animation	loading
	members.service.ts	modify getMember() getMembers() and updateMembers() to implement signals and cache	B1		Commit a4b56cc	API.csproj	added cloudinary package
	app.component.html	add spinner for testing	loading			ApplicationServiceExtensions	Added Photo Service and Configured Cloudinary
	app.component.ts	add spinner import to ts file	loading			CloudinarySettings.cs	added Cloudinary model (its a helper)
	app.config.ts	add loading interceptor to providers, and import providers for loading animation	loading			IphotoService.cs
	Member-edit-component.html	changed text	B2 I			PhotoService.cs	AddPhotoAsync(), DeletePhotoAsync()
	Member-edit-component.ts	updateMember() now calls the member.service updateMember() method	B2 ii
	Member-list.comonent.html	user the member service members() signal on member-list component to provide a list of members	B3
	Member-list-component.ts	use the signal to check if loading members is necessary	B3

	ADDED NGX SPINNER TO				STOPPED TRACKING APPSETTINGS.JSON
		angular.json
		packaage.json (via CLI)			CLOUDINARY CONFIGURATION
	ADDED THE INTERCEPTOR AND BUSY SERVICE					appsettings.json (not commited)
		loading.interceptor				added cloudinary package
		busy.service				CloudinarySettings.cs
	ADDED THE SPINNER TO THE MAIN COMPONENT					ApplicationServiceExtensions
		app.component html and ts			ADDED PHOTO SERVICE (ADAPTED TO FREELANCER MARKETPLACE)
	ADDED A HEADER TO SERVICES (HTTP CALLS)					IphotoService.cs
	WHERE I WANT TO SKIP THE SPINNER					PhotoService.cs
		members.service
		account.service

## D14
CLOUDINARY IMPLEMENTATION

BASE FILE TO STUDY TO ADAPT TO IMPLEMENTATION					HAD TO REFACTOR RELATIONSHIPS BETWEEN
					PHOTO AND PROJECT AND PHOTO AND PORT.ITEM
d7472b9	Updating Users Controller, Photo Upload, Photo Editor Component, Photo Uploader, Setting the Main Photo in the API, Adding Main Photo to Nav Bar, Setting Main Photo in Client, Deleting Photo in the API, Deleting Photo in Client	wonderPhoto.png	added photo to assets					ONE TO ONE
		wonderPhoto3.png	added photo to assets					MODIFIED SEED.CS
		AccountController.cs	included photos model in user model in Login(), improved UserDTO					MODIFIED MAPPINGS FOR USER
		UsersController.cs	Added PhotoService, modified updateUser(), AddPhoto(), SetMainPhoto(), DeletePhoto()					PERFOMED MIGRATIONS AFTER MODIFYING ENTITIES
		UserDTO.cs	added photourl property					AND DATA CONTEXT
		ClaimsPrincpleExtensions.cs	GetUsername()			This method is typically used in API controllers or services to get the username of the currently authenticated user from the JWT token

BACKEND WORK

Test-photo-portfolio-item			add to assets
Test-photo-project			add to assets
Test-photo-user-freelancer (female)			add to assets
Test-photo-user-client (male)			add to assets

AccountController.cs			Lazy Loading + set Photo Url
ClaimsPrincpleExtensions.cs			Refactor Get Username
UserDTO.cs			Add Photo Url
UsersController.cs			Inject Photo Service + Refactor Claims Principle GetUsername()
			AddPhoto (post endpoint) (go line by line)
		may not be necessary	SetMainPhoto => SetPhoto (post endpoint) (go line by line)
			DeletePhoto (delete endpoint)
Ask ChatGPT if AddPhoto SetPhoto and DeletePhoto are endpoints in the Users Controller in legacy,					CREATED PHOTO CONTROLLER
	but shouold appear also in PortfolioItemController and ProjectController… should
	they be extracted to their own controller?

## D15
				CLOUDINARY INTEGRATION WITH THE FRONT END
To keep it simple					package.json	added ng2-file-upload dependency with overrides since the package has not been updated property by the vendor
				user.ts	added photourl to the model
see last conversation about this					account.service.ts	extracted repeated functionality to setCurrentUser(),
single file upload doesn’t require any package					members.service.ts	setMainPhoto(), deletePhoto()
can be implemented in profile edit, port item create and proj create					app.component.html	modified loading indicator (spinner) style
components					Member-detail.component.html	modified gallery tag
can be sent with the form and processed in two separate endpoints					Member-edit-component.html	added photo-edit component
				Member-edit-component.ts	onMemberChange()
				Photo-editor-component.css	added styles
				Photo-editor-component.html	added skeleton to photo editor component
				Photo-editor-component.ts	fileOverBase(), deletePhoto(), setMainPhoto() initializeUploader()
				nav.component.css	added styles
				nav.component.html	added photo of current user to nav bar

Implemented Photo Update and Deletion for Clients and Freelancers (Profile, Profile Edit Client, Profile Edit Freelancer Components),
and for Portfolio Items and Projects (Porfolio Item Create and Project Create Components),
Implemented the Photo Service and made Modifications in the Client and Freelancer Nav Bars to Display the Profile Photos

				FRONT END WORK

				package.json	added ng2-file-upload dependency with overrides since the package has not been updated property by the vendor
				1	user.ts	added photourl to the model
				1	account.service.ts	extracted repeated functionality to setCurrentUser(),	REFACTOR
				2	members.service.ts	setMainPhoto(), deletePhoto()
				1	app.component.html	modified loading indicator (spinner) style	SIMPLE
				2	Member-detail.component.html	item auosize on hmtl – not sure its necessary
				2	member edit => profile edit / portfolio item create / project create	tag app photo editor with input and outputs
				2	member edit => profile edit / portfolio item create / project create	ts file changes

				2	photo editor component	adapt
				2	photo editor component	adapt

				1	nav component css	styles
				1	nav html	display image

## Future through 32
	Wireframes				Dating App

					THIS IS NEXT UPON RETURN FROM CHILE:
15 (NOW 16)					Improve Registration Form and Process Validation
16					Pagination Functionality
17	Browse Projects (FL) page
17	Browse Projects (FL) page with Filters				Filters
18 19	Browse Projects (FL) page (Submit Proposal)				Likes Functionality (Accepting Proposals) -ask AI because I think like functionality has nothing to do in this application
20	Active Projects page (FL) (CL)
21 22	Messaging Page (FL) (CL)				Messaging Backend
23					Messaging Front End
24					Review Roles
24					Admin Panel
25					Modals
26 27 28	Chat Page (FL) (CL)				Presence Hub and Signal R
29					Message Notification
30	NEW Sent Proposals Page (FL)
30	Proposal Inbox (similar to above) (CL)
31	Accept or Reject Proposals (CL) in Proposal Inbox
32					Approving Photos and so on (Admin Functionality) – may not apply + Unit of Work